## Read me
Khas Tracker risk register (review copy)
As of 2026-10-31. Method: 01-risk/methodology.md (NIST SP 800-30 Rev 1, ISO 27001 6.1.2 / 6.1.3).
How to review
1. Go to the Risks sheet. Each row is one risk. Use the filter arrows to sort by Current level.
2. Blue numbers are inputs: likelihood (L) and impact (I), 1 = Very Low ... 5 = Very High. Change one and the score and level recalculate.
3. Fill in the two yellow columns at the far right: "Your decision" (Agree / Change) and "Your notes" (what to change and why).
4. Rows already marked "Decided by M. Khas" were decided in chat; you can still change them.
Columns
Score = L x I (1-25), only for sorting. Level = SP 800-30 Table I-2 lookup (see Scales sheet). The level drives decisions.
Inherent = without Khas Tracker's own controls. Current = with verified controls today. Target = after the planned action.
Example row: R-01. Inherent L 4, I 5 -> score 20, Very High. Current L 2, I 5 -> 10, Moderate. Target L 1, I 5 -> 5, Low.
Source of truth: 01-risk/risk-register.csv. This workbook is generated from the same data for easier review.

## Risks
Risk ID | Risk | Threat event | Threat sources | MITRE ATT&CK | Assets | Vulnerabilities / conditions | Existing controls (verified) | Scoring rationale | Inherent L | Inherent I | Inherent score | Inherent level | Current L | Current I | Current score | Current level | Treatment | Planned action | Target L | Target I | Target score | Target level | Owner | Status | Next review | Your decision | Your notes
R-01 | Administrator identity or credential store compromised | An attacker gains the administrator's AWS credentials and second factor through phishing, a compromised identity account or a stolen unlocked device, and takes control of the AWS account, including the ability to delete data and backups | TS-01; TS-02 | T1566; T1555; T1078.004; T1485; T1496 | A-08; A-09; A-01; A-02 | V-01; V-06; V-07; V-08; V-14 | MFA on AWS root and admin user; MFA on administrator identity accounts; no AWS access keys on the operator's computer (CloudShell only); budget alerts | Likelihood Low: MFA blocks password-only attacks, but the factors are not independent, so one compromise can yield both. Impact Very High: full control of production and backups | 4 | 5 | 20 | Very High | 2 | 5 | 10 | Moderate | Mitigate | Move AWS root and admin MFA to phishing-resistant factors (security keys or passkeys) kept outside the password store; lock backups against deletion (AWS Backup Vault Lock); test admin recovery (with R-19) | 1 | 5 | 5 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-04-30 | Agree
R-02 | Malicious deploy through a compromised identity or code-host account | An attacker takes over the identity account that signs in to the code host, pushes a change to main, and the pipeline deploys an app that captures users' passphrases | TS-01; TS-02 | T1078; T1195.002; T1056.003 | A-06; A-05; A-09; A-01 | V-02; V-03; V-06 | MFA on the code host and identity account; deploy role usable only from the main branch of one repository; 1-hour deploy sessions; full Git history of every change | Likelihood Low: MFA on both accounts, but no approval step stands between a push and production. Impact Very High: every user's data readable from then on (breaks SC-1) | 4 | 5 | 20 | Very High | 2 | 5 | 10 | Moderate | Mitigate | Phishing-resistant MFA (passkey or security key) on the identity account and code host; give the code host its own sign-in; email notification on every production deploy; review the code host security log monthly | 1 | 5 | 5 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-04-30 | Agree
R-03 | Unreviewed change breaks the app or corrupts data | The operator pushes a faulty change (for example a sync or encryption bug) that deploys straight to production and breaks the app or damages stored records | TS-06; TS-07 |  | A-05; A-01; A-11 | V-03; PC-01 | CI runs unit tests and a type check before every deploy; deploys only from main; rollback by revert; DynamoDB deletion protection and point-in-time recovery; encrypted copies on users' devices | Likelihood Moderate: frequent solo changes with no second review. Impact Moderate: point-in-time recovery and device copies limit lasting loss | 4 | 5 | 20 | Very High | 3 | 3 | 9 | Moderate | Mitigate | Work on branches with a pull request and a self-review checklist; CI runs on pull requests before merge; each merged PR is the change approval record | 2 | 3 | 6 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-04-30 | Agree
R-04 | Operator ships a passphrase-capturing build | The operator, deliberately or under pressure, deploys app code that captures users' passphrases | TS-05 | T1056.003 | A-05; A-01 | PC-01; PC-02 | Git history makes any code change visible after the fact; users know the operator personally | Likelihood Very Low: no motive and personal relationships with every user. Impact Very High: all content readable | 1 | 5 | 5 | Low | 1 | 5 | 5 | Low | Accept | Accepted at design time: the risk cannot reach zero while the operator serves the code, even with a second person. Add a free detective control: a changelog of every production deploy that users can see. Re-assess if a second admin is added (T-06) or users who are not friends or family join (T-04) | 1 | 5 | 5 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-10-31 | Agree | I think agree? The only way this could be mitigated is if I had a second person right? If there is any other way to absolutely mitigate this, I would love to implement.
R-05 | Malicious dependency or Action runs in the deploy job | A compromised npm package or GitHub Action runs inside the deploy job, uses the deploy credentials, and changes the app or the AWS account | TS-03 | T1195.001; T1078.004 | A-06; A-07; A-08; A-05 | V-04; V-05 | Small direct dependency set (2 runtime, 5 development packages); no long-lived AWS keys in CI (OIDC); 1-hour sessions; deploy role limited to main; CI tests | Likelihood Low: supply-chain attacks are common but untargeted, and the direct dependency set is small; the transitive tree is much larger. Impact Very High: the deploy role is administrator-equivalent | 3 | 5 | 15 | High | 2 | 5 | 10 | Moderate | Mitigate | Commit a lockfile and install with npm ci; give the deploy credentials only to the deploy step; pin GitHub Actions to commit SHAs; turn on Dependabot alerts; later, narrow the CDK deploy permissions | 1 | 5 | 5 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-04-30 | Agree
R-06 | Incident goes undetected or cannot be investigated | An attack or misuse in the AWS account or app is not noticed, or cannot be reconstructed afterwards because the needed logs do not exist | TS-01; TS-02; TS-03; TS-05 | T1562.008 | A-12; A-08 | V-06 | Budget alerts; AWS CloudTrail event history (AWS default, 90 days, management events); Lambda error logs (14 days) | Likelihood Moderate: no security alerting at all today. Impact High: affected users could not be told what was exposed | 4 | 4 | 16 | High | 3 | 4 | 12 | Moderate | Mitigate | Free controls only (no GuardDuty, a cost decision): verify or create a CloudTrail trail with log file validation; free email alerts on root and admin sign-in and on logging changes; keep app logs longer. Remaining Moderate risk to be accepted with a written reason after treatment | 3 | 4 | 12 | Moderate | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-04-30 | Agree
R-07 | User account taken over | An attacker or someone close to a user gets their password and authenticator code (phishing, reuse, access to their phone) and signs in as them | TS-01; TS-04 | T1566.002; T1078; T1111; T1485 | A-04; A-01 | V-12; V-13 | Invite-only accounts; TOTP MFA required; 10-character minimum password; generic sign-in errors; 1-hour tokens; API throttling; end-to-end encryption means a taken-over account exposes only ciphertext | Likelihood Low: MFA required and a small, invite-only user base. Impact Moderate: the attacker gets ciphertext only but could delete that user's records (recoverable) | 4 | 4 | 16 | High | 2 | 3 | 6 | Low | Mitigate | Move the user pool to the Cognito Essentials plan (free under 10,000 monthly users) and offer passkey sign-in, which resists phishing; tell users how to protect their account in the Phase 6 privacy notice | 1 | 3 | 3 | Very Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-10-31 | Agree | Is this where we could mitigate by having anoption to download an offline copy of their data? How coud we mitigate this if we wanted to.
R-08 | Passphrase cracked offline | Someone who already holds a user's keyring (for example after an AWS breach) guesses a weak passphrase offline and decrypts that user's data | TS-01; TS-02; TS-05 | T1110.002 | A-01; A-02 | V-15 | PBKDF2-SHA256 with 600,000 iterations; passphrase at least 12 characters; 24-character random recovery code; keyring reachable only after another compromise (R-01, R-02, R-05) | Likelihood Very Low: needs a prior AWS compromise plus a weak passphrase. Impact High: one user's content | 3 | 5 | 15 | High | 1 | 4 | 4 | Low | Mitigate | Add a self-hosted passphrase strength check (block common passphrases, encourage several words), with no third-party scripts | 1 | 4 | 4 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-10-31 | Agree | yeah, if a passphrase strength meter is the best we can do, we should do that.
R-09 | Record metadata shows when users log | The operator, AWS or anyone who reaches the table sees record names and timestamps that show which days each user logged something | TS-05; TS-01 | T1530 | A-03 | V-09; PC-03 | Only record names, timestamps and sizes are visible, never content; table access limited to the operator | Likelihood Moderate: the operator sees metadata whenever doing support. Impact Moderate: activity dates of several users | 3 | 3 | 9 | Moderate | 3 | 3 | 9 | Moderate | Mitigate | Change how records are named so stored keys no longer reveal dates (for example, keys derived with the user's data key); only sync timestamps would remain. Engineering change in the app | 3 | 2 | 6 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-04-30 | Agree
R-10 | Deleted users remain in backups for years | A user leaves and asks for deletion, but encrypted copies of their data stay in backups for up to 3 years | TS-10 |  | A-02; A-14 | V-10; V-11 | Backups hold ciphertext only, unreadable without the user's passphrase | Likelihood Moderate: someone among 10 users may leave in a given year. Impact Low: data is unreadable; harm is to trust and promises | 3 | 2 | 6 | Low | 3 | 2 | 6 | Low | Mitigate | Retention schedule and plain disclosure in the privacy notice (Phase 6); decide whether 3-year copy retention is needed | 2 | 2 | 4 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-10-31 | Agree | Mitigate
R-11 | Privacy obligations not met | A user or a person they record complains, or a law applies, and there is no notice, terms or record of how requests were handled | TS-10 |  | A-14 | V-11; PC-03; PC-04 | Users are known personally; content is end-to-end encrypted; commitments made in the invitation email and setup screens | Likelihood Low: friends and family are unlikely to complain formally. Impact High: formal complaint or consumer health law exposure (trigger T-03) | 2 | 4 | 8 | Low | 2 | 4 | 8 | Low | Mitigate | Privacy notice and terms, a request log, and the applicable-law analysis including non-user data (Phase 6) | 1 | 4 | 4 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-10-31 | Agree | Mitigate
R-12 | User data permanently lost | A bug, an admin mistake (such as deleting the wrong account) or an AWS fault destroys records, and the restore fails or was never practised | TS-06; TS-07; TS-08 |  | A-01; A-02 | V-07 | Point-in-time recovery (35 days); daily backups (35 days) with a cross-region copy (3 years); table deletion protection; encrypted copies on users' devices | Likelihood Low: several independent copies exist, but restore has never been recorded as tested. Impact High: a user's history lost for good | 3 | 5 | 15 | High | 2 | 4 | 8 | Low | Mitigate | Run and record a restore test at least yearly; bring the copy vault into infrastructure code or document it; backup lock (with R-01) | 1 | 4 | 4 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-10-31 | Agree | Mitigate
R-13 | Operator unavailable for an extended period | The operator cannot run the service for weeks (illness, life events); nobody else can fix problems, help users or keep the account paid | TS-09 |  | A-13 | PC-01 | Serverless service runs without intervention; domain auto-renews; backups are automatic; users keep encrypted copies on their devices | Likelihood Low. Impact High: an outage of more than a week is possible and users have no way to export their data | 2 | 4 | 8 | Low | 2 | 4 | 8 | Low | Mitigate | A short continuity note for a trusted person (what to tell users, how to shut down cleanly); turn the user backup download back on | 2 | 3 | 6 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-10-31 | Agree | Mitigate
R-14 | Outage or cost spike | An AWS fault, a traffic flood or abuse of the API makes sync unavailable or runs up the bill | TS-01; TS-07; TS-08 | T1499 | A-11; A-05 | PC-06 | App works offline and syncs later; API throttling (10 requests/second, burst 20); CloudFront in front of all traffic; AWS Shield Standard (provided by AWS); budget alerts | Likelihood Moderate: regional AWS issues happen. Impact Low: the app keeps working offline | 3 | 3 | 9 | Moderate | 3 | 2 | 6 | Low | Accept | Accept; within the moderate appetite for outages | 3 | 2 | 6 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-10-31 | Agree | Accept
R-15 | Domain or DNS hijacked, or domain lapses | The domain is transferred, its DNS changed or it expires, and users are sent to a fake app that captures passphrases | TS-01; TS-02; TS-06 | T1584.001; T1056.003 | A-10 | V-14 | Registration and DNS protected by AWS account controls (R-01); auto-renew on; HSTS for one year; TLS certificate validated by DNS | Likelihood Very Low: needs an AWS compromise or a registrar failure. Impact Very High: a fake app could capture passphrases | 2 | 5 | 10 | Moderate | 1 | 5 | 5 | Low | Mitigate | Free checks under the confidentiality rule (methodology 4.2): verify registrar transfer lock, auto-renew, contacts and renewal payment, and add them to the Phase 4 automated checks. Residual risk cannot reach zero; the aim is verified controls with evidence | 1 | 5 | 5 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-10-31 | Agree | Mitigate, and we need to validate that this CANNOT happen.
R-16 | User mailbox exposes invitation password or recovery code | Someone with access to a user's mailbox uses the temporary password or a self-emailed recovery code | TS-01; TS-04 | T1114 | A-04; A-01 | V-13 | Temporary password expires in 7 days and must be changed; TOTP still required to sign in; a recovery code alone cannot sign in | Likelihood Low. Impact Low: the attacker still needs the user's authenticator to reach any data | 3 | 4 | 12 | Moderate | 2 | 2 | 4 | Low | Accept | User guidance on storing the recovery code in the Phase 6 privacy notice | 2 | 2 | 4 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-10-31 | Agree | Accept
R-17 | Client-side code flaw exposes plaintext | A flaw such as cross-site scripting lets an attacker run script in the app and read decrypted data in the browser | TS-01 | T1189; T1059.007 | A-05; A-01 |  | Strict Content Security Policy (scripts only from the app's own origin, no inline scripts); no third-party scripts or frameworks; framing blocked; no referrer sent | Likelihood Very Low: strict CSP and no third-party code. Impact Very High: plaintext readable in the browser | 3 | 5 | 15 | High | 1 | 5 | 5 | Low | Mitigate | Add Trusted Types to the Content Security Policy (require-trusted-types-for 'script'), free under the confidentiality rule; keep the CSP strict and re-assess if any third-party script or framework is added | 1 | 5 | 5 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-10-31 | Agree | I don’t want to accept this if I don’t want to, or are we saying that this isn't actually an issue?
R-18 | API authorization flaw between users | A flaw in the sync API lets one user read, change or delete another user's records | TS-04; TS-01 | T1190 | A-11; A-01 |  | JWT required on every API route; Lambda takes the user ID only from the verified token; user ID and record key bound into each ciphertext; API unit tests | Likelihood Very Low: the user ID never comes from the request body. Impact Moderate: content stays encrypted; records could be altered or deleted | 3 | 4 | 12 | Moderate | 1 | 3 | 3 | Very Low | Mitigate | Add cross-user tests for the two API routes not yet covered (single-record read and delete), so every route is checked on every deploy | 1 | 3 | 3 | Very Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-10-31 | Agree | I don’t want to accept this if I don’t want to, or are we saying that this isn't actually an issue?
R-19 | Operator locked out of administration | The operator loses their phone and cannot get back into AWS or the code host because recovery has never been tested | TS-06; TS-08 |  | A-09; A-08 | V-01; V-08 | Account recovery options on the identity accounts; AWS root account recovery process (provided by AWS) | Likelihood Low. Impact High: no fixes or account changes possible for more than a week | 3 | 4 | 12 | Moderate | 2 | 4 | 8 | Low | Mitigate | Test recovery of administrator access from a new device; keep printed break-glass recovery codes stored offline | 1 | 4 | 4 | Low | M. Khas | Decided by M. Khas, 2026-10-31 | 2027-10-31 | Agree | Mitigate
Note on AA1: Agree = keep as proposed. Change = explain in Your notes.

## Scales
Likelihood (within 12 months)
Value | Level | Definition
5 | Very High | Almost certain. More than once a year
4 | High | Likely. About once a year
3 | Moderate | Could happen. About once every 1-3 years
2 | Low | Unlikely. About once every 3-10 years
1 | Very Low | Highly unlikely. Less than once in 10 years
Risk level matrix (SP 800-30 Table I-2). Rows = likelihood, columns = impact
| Likelihood \ Impact | Very Low (1) | Low (2) | Moderate (3) | High (4) | Very High (5)
5 | Very High (5) | Very Low | Low | Moderate | High | Very High
4 | High (4) | Very Low | Low | Moderate | High | Very High
3 | Moderate (3) | Very Low | Low | Moderate | Moderate | High
2 | Low (2) | Very Low | Low | Low | Low | Moderate
1 | Very Low (1) | Very Low | Very Low | Very Low | Low | Low
Impact: rate the worst effect on people, the service or the operator. Full scale in methodology.md section 3.2.

## Assets
ID | Asset | Includes | C | I | A | Why it matters
A-01 | User content and keyrings | D-01 to D-10, D-13, stored as ciphertext in DynamoDB | High | High | Moderate | Health, mental health, religious and third-party data. Promise SC-1 depends on it
A-02 | Backups | Point-in-time recovery (35 days), daily backup vault (35 days), copy vault in a second region (3 years) | High | High | High | The only way back from data loss. Also holds deleted users' data
A-03 | Record metadata | D-21: record names, timestamps, sizes | Moderate | Low | Low | Readable by the administrator and AWS. Shows when users log, not what
A-04 | User accounts | D-15 to D-20 in Cognito | Moderate | High | Moderate | Gate to each user's ciphertext and the ability to delete it
A-05 | Web app as delivered | D-27: files in S3 served by CloudFront | Low | Very high | Moderate | Whoever controls these files controls the code that handles passphrases
A-06 | Source code and deploy pipeline | D-26: private GitHub repository and Actions workflow | Moderate | Very high | Low | A push to main deploys to production
A-07 | Deploy identity | GitHub OIDC deploy role and the CDK bootstrap roles it uses | n/a | Very high | Low | Can change any resource in the stack
A-08 | AWS account | Root user, administrator IAM user, billing, account-level settings | n/a | Very high | High | Full control of everything above
A-09 | Administrator identities and credential store | D-25: password manager and personal identity accounts used to reach AWS and GitHub (D-008) | Very high | Very high | High | The real perimeter for a one-person operation
A-10 | Domain, DNS and email identity | Domain registration, DNS zone, TLS certificate, SES sending domain | n/a | Very high | High | Controls where users' browsers go and who can send mail as the app
A-11 | Sync API | API Gateway and Lambda | n/a | High | Moderate | Enforces per-user access to records
A-12 | Logs and audit trail | Lambda logs (14 days); account-level audit logging (unverified) | Low | High | Moderate | Needed to detect and investigate an incident
A-13 | The operator | One person who builds, runs and supports the service | n/a | n/a | High | Nobody else can operate the service
A-14 | Privacy commitments and request handling | Commitments SC-1 to SC-5; D-24 support requests | n/a | n/a | n/a | How users' rights and expectations are met

## Threat sources
ID | Threat source | SP 800-30 type | Capability | Intent | Targeting | Notes
TS-01 | Opportunistic outsider (phishing kits, credential stuffing, bots) | Adversarial: individual or group, outsider | Moderate | Money: resell accounts, mine crypto, ransom | Low. Hits anyone | The most common real-world source for small cloud accounts
TS-02 | Targeted outsider | Adversarial: individual, outsider | Moderate | Personal: someone who knows the operator or a user | Moderate | Unlikely, but the users are a small, known group
TS-03 | Software supply-chain attacker | Adversarial: group, established | High | Broad credential and code theft | Low. Hits whoever installs the package | Compromised npm packages or GitHub Actions
TS-04 | Trusted insider: a user, or someone close to one | Adversarial: individual, trusted insider | Low | Curiosity, relationship conflict | High. One specific person | For example, a partner with access to a user's unlocked phone
TS-05 | Privileged insider: the operator, acting deliberately or under pressure | Adversarial: individual, privileged insider | Very high | None today. Included because the trust model depends on it | n/a | See R-04
TS-06 | The operator's own mistakes | Accidental: privileged user or administrator | n/a | n/a | n/a | Wrong command, bad deploy, misconfiguration
TS-07 | Software and service faults | Structural: software, IT equipment | n/a | n/a | n/a | Bugs in the app or in AWS services
TS-08 | Infrastructure outage or disaster | Environmental: infrastructure failure | n/a | n/a | n/a | AWS region outage; loss of the operator's phone or computer
TS-09 | Operator unavailable | Added: not in Table D-2 (key person) | n/a | n/a | n/a | Illness, travel, life events
TS-10 | Legal and regulatory | Added: not in Table D-2 | n/a | n/a | n/a | A complaint, regulator inquiry or new law. ISO 27001 clause 4.2 brings these in

## Vulnerabilities
ID | Vulnerability | Assets | Source | Status
V-01 | Administrator sign-in factors are not fully independent of each other | A-08, A-09 | Phase 0 interview | Open
V-02 | A personal identity account can sign in to the code host, and the code host deploys production with no approval step | A-06, A-09 | Phase 0 interview; deploy.yml | Open
V-03 | No branch protection or second reviewer on the app repository | A-06 | Phase 0 interview | Open
V-04 | The deploy role can use the CDK bootstrap roles, which have broad (administrator-equivalent) permissions | A-07, A-08 | tracker@9124656:infra/lib/tracker-stack.ts:359-362 | Open
V-05 | The CI pipeline doesn't pin dependencies to a lockfile, pins GitHub Actions to version tags rather than commits, and has no dependency scanning | A-06, A-07 | tracker@9124656:.github/workflows/deploy.yml:25-33 | Open
V-06 | Account-level audit logging and threat detection are unverified; app logs are kept 14 days; no API or CDN access logs | A-12 | System description 3.1; tracker-stack.ts:190-193 | Open (unverified)
V-07 | The backup copy vault was created by hand outside infrastructure code; backups are not locked against deletion; no restore test is on record | A-02 | tracker-stack.ts:306-316; DEPLOY.md Part 6 | Open
V-08 | Recovery of administrator access after losing a device has not been tested | A-09, A-08 | Phase 0 interview | Open
V-09 | Record metadata is stored unencrypted | A-03 | tracker@9124656:infra/lambda/api.mjs; data inventory D-21 | By design
V-10 | Backup retention (up to 3 years) is set by a technical setting, not a retention decision, and is longer than a user would expect after deletion | A-02, A-14 | tracker-stack.ts:322 | Open
V-11 | No privacy notice, terms, or log of user requests | A-14 | System description 2, 3.4 | Open (Phase 6)
V-12 | User sign-in uses the Cognito Lite plan (no compromised-credential or risk-based checks); password policy is length-only, 10 characters | A-04 | tracker-stack.ts:132-141 | Open
V-13 | Invitations carry a temporary password by email; users may email themselves their recovery code | A-04, A-01 | tracker-stack.ts:87-94; data flow 9, 10 | By design
V-14 | Domain registration and DNS live in the same AWS account as the app and an unrelated personal site; registrar transfer lock unverified | A-10 | System description 3.1; D-007 | Open (unverified)
V-15 | Data passphrase strength is checked by length only (12 characters) | A-01 | tracker@9124656:web/js/app.js:32 | Open

## Conditions
ID | Condition | Effect on risk
PC-01 | One operator does everything | No separation of duties or independent review; key-person dependency
PC-02 | The operator controls the code that handles users' passphrases | End-to-end encryption protects stored data from the operator, but not from a changed app
PC-03 | Most data is special-category, and some is about people without accounts | Raises the impact of any confidentiality breach
PC-04 | Users are friends and family | Informal communication; lower likelihood of complaints; higher personal cost if trust breaks
PC-05 | Near-zero budget | Favours free controls; paid tools need a clear risk case
PC-06 | The app works offline and keeps an encrypted copy on each device | Lowers the impact of outages and of some data loss
PC-07 | All user content is end-to-end encrypted | Lowers the impact of most server-side compromises to metadata and availability